## Sheet1
Mobile World
Date | 08.01.2013
Time | (09:00-10:30)AM
Participants | Client Name: Geetha
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Get to know the Project | Listed out various sites for reference
Finalised on a plan of implementing the website
A consensus made on the name of "MobileWorld"
Discussion Details | Project to be implemented usng 3 modules(Buyer,Seller,Admin)
Buyer searches for a specific product and may or maynot order it
Seller adds a new product with his price and waits for the review from Admin
Admin can review a product and add to the website
Date | 09.01.2013
Time | 9:00:00 AM to 5:00:00 PM
Participants | Client Name: Geetha
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Use Case Diagram | Each and every process must be described in a separate Use Case diagram
Functional Decomposition Diagram | Functional Decomposition Diagram was drawn according to the specification
Software Requirement Specification | Software Requirement Specification has been developed by each and every individual modules and then combined according to the project specification
Project Planning | Project plan have been discussed by all our project team members and then finalised to show to our clients
Screen shots | Screenshots have been prepared accordingly and grouped together
Date | 29.01.2010
Time | 9:00:00 AM to 5:00:00 PM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Validating address | Validating address using the postal code, street number and city.
design diagrams | draw architectural diagrams, and the data flow diagram..
regarding concurrent no of users | call center can support 50 seater user's concurrently..
This call centre module depends upon duration, so need to use concurrent user
Date | 30.01.2010
Time | 9:00:00 AM to 11:00:00 AM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
SRS Review | Done clarifications regarding user profiles that roles must be clearly mentioned
Done clarifications regarding volumetric data that number of users should be mentioned properly
Here Data Migration is not applicable and its integration
Requirement specification has been clarified with our client
Functional requirements has been clarified with our client
Discussed about Database requirements,Operational Requirements,Software Interface
Discussed about response time that it should be reasonable
User manual shall be provided by developer
In acceptance criteria about the license duration
Regarding the screen shots, screen shots is only a sample prototype and it can be changed at the design level.
Regarding the Login screen - about the user type, first name, last name, middle name, confirmation email
Regarding the Recall and replacement module interface with our module
user interface can be an exe file, or can create separate database for the logistics company
Buttons used in the prototype can be image buttons
Hundred thousand of defective keyboard adapter's were sold.
Design Diagrams | Architectural diagram, class diagram, dfd diagram
Date | 01.02.2010
Time | 9:00:00 AM to 11:15:00 AM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Regarding Design Diagrams | Need to add deployment diagram, traceability matrix,
State diagram can be drawn if needed
Date | 02.02.2010
Time | 9:00:00 AM to
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Design Document Review | Discussed about the design document checklist
It is mainly about the architecture, interfaces, design pattern, user interface, all requirement must be addressed,design is a direction to developer
In class diagram, fields should be mentioned clearly and constructor should not be used if class diagram is static model
In sequence diagram, it should come first in the design document and transaction should be mentioned with functions
Need to mention about the session to store login information
In Deployment diagram, Email automation should be mentioned
In architectural diagram, Need to change from interface class to proxy class
Login page of all the modules can be same since it can be reusable
Sequence Diagram | To split the sequence diagram according to methods and classes used.
Date | 03.02.2010
Time | 9:00:00 AM to 9:30:00 AM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Design Document | Discussed about the date of the review
Coding | Started coding according to the module and coding standard
To add the First name and last name field in the Serial number validation page
Date | 04.02.2010
Time | 9:30:00 AM to 10:05:00 AM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Coding | Discussed about the coding concepts and client gave us hint regarding what we need to do for our module
Coding Review | store connection string in the xml file
Event log must be specified for database
Value must be assigned before checked in the session
need to use persistent cookie
need to change authentication mode to forms
checking of username and password in the session and need to use unique null
Need to change message box since users will not be able to see it on their end
Instead of message box need to use java script alert message
Need to include first name and last name in the serial number validation page
Need to change validateonserialnumber to searchonserial number
Need to create a web application project instead of wesite
Date | 05.02.2010
Time | 3:15:00 PM to 3:30:00 PM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: Bharath Pillai,Gaurav Dhavale,Paulami Banerjee,Sachin Mandal,Marunidevi
Item | Response / Decision | Due Date
Web Services | Discussed about the webservices and the remote machine connection
Regarding the design module, discussed about the design overview for the web page
Decided about the last date of completion for code submission
Date | 06.02.2010
Time | 3:20:00 PM to 5:05:00 PM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: A.Vanitha, P. Narayanan, R.Rajesh Kumar, J. Divya, S.P.Meenu
Item | Response / Decision | Due Date
Deliverables | regarding the completeness
SRS | regarding the completeness
Design Document | Cannot have fields and completeness were discussed
traceability matrix | up to date completeness
Unit testing and system testing | need to done with sample document
Sample data document | shoyuld be there for each and every testing
Code-class files | discussed about the class files in the code
Comments | should be specified in each and every modules and specification
Completeness of the code | discussed about code completeness
Traceability matrix | discussed about the completeness
Test plan | Need to maintain test plan
Peer communication | Need to check each and every document with all our team members
Error Log | Error log have to be maintained
Implementing a Library component | Components apart from class like libraries should be implemented
Next review | on Monday
Date | 08.02.2010
Time | 2:30:00 PM to 3:00:00 PM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: A.Vanitha, P. Narayanan, R.Rajesh Kumar, J. Divya, S.P.Meenu
Item | Response / Decision | Due Date
Additional requirement | Company is providing additional services to the customers such as Microphone, Amplifier speaker and stand accesssories
Call centre module should create a database to maintain new records for the customer.
Email should be sent to the customer regarding the purchase
Regular customer can be offerred 20 percent discount
Date | 09.02.2010
Time | 2:30:00 PM to 3:00:00 PM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: A.Vanitha, P. Narayanan, R.Rajesh Kumar, J. Divya, S.P.Meenu
Item | Response / Decision | Due Date
Presentation | Discussed about the presentation slides and its content
The presentation slides can be 10 slides at maximum and should be crisp and clear
Deployment | Client told us to create a setup for the project
Date | 10.02.2010
Time | 10:00:00 AM to 10:25:00 AM and 2:10:00 PM to 2:40:00 PM
Participants | Client Name: Mr.Srinivasan Iyer
Team Members: A.Vanitha, P. Narayanan, R.Rajesh Kumar, J. Divya, S.P.Meenu
Item | Response / Decision | Due Date
Presentation | Discussed about the new presentation template given today
Discussed about the phases of that template
Coding | Discussed about the Error log and its functions